## Sheet1
Task | Assigned to | Start Date | Finish Date | Work (in hours) | Notes
Group meeting to discuss project components, strategy and roles | MB, HH, WE | 2018-09-11 | - | 1
Introduce a number of tools to help in planning, sharing and implementation | MB | 2018-09-11 | 2018-09-11 | 1 | GitHub, Trello, draw.io, OneDrive
Prepare project plan | WE | 2018-09-12 | 2018-09-14 | 3
Write program purpose | MB, HH, WE | 2018-09-12 | 2018-09-14 | 3
Prepare program structure | WE | 2018-09-12 | 2018-09-14 | 3 | diagram/flowchart using draw.io tool
Prepare UI description | HH | 2018-09-12 | 2018-09-14 | 3
Write program code | MB | 2018-09-14 | 2018-09-19 | 6
Write testing report | MB | 2018-09-14 | 2018-09-19 | 6
Write user manual | HH, WE | 2018-09-14 | 2018-09-19 | 6
Prepare report structure | WE | 2018-09-16 | 2018-09-16 | 2
Group meeting to review project plan, purpose, structure, UI description | MB, HH, WE | 2018-09-14 | - | 1
Group meeting to review the code and testing report | MB, HH, WE | 2018-09-17 | - | 1
Project meeting to show progress | MB, HH, WE | 2018-09-21 | - | 1 | code, draft project plan, program purpose and structure
Review and finalize the report | WE | 2018-09-25 | 2018-09-26 | 4
Meet with opponent group to understand their project and explain ours | MB, HH, WE | 2018-09-24 | 2018-09-25 | 2
Project submission on student portal | MB, HH, WE | 2018-09-27 | - | 1
Prepare opposition report | HH, WE | 2018-09-27 | 2018-09-27 | 4
Group meeting to finalize the report and prepare for presentation of opponent group | MB, HH, WE | 2018-09-27 | - | 1
Presentation of opponent group | MB, HH, WE | 2018-09-28 | - | 1
Group Members | Initials
Mikhail Boronin | MB
Hongyu He | HH
Wafaa Elbaghdady | WE